## Guidance notes
SPORT WALES PROJECT DELIVERY PLAN TEMPLATE
Use the 'EXAMPLE - Project Plan' sheet to amend and create a project plan which will work for you. The text within the template is only there for the purpose of providing an example - edit and use as necessary to work for you. For example you may want to substitute "Sprint 1" for "Quarter one" or "January" and list the key tasks that fit under that time period. By adding dates against a task, you will automatically update the Gantt chart on the bottom of the sheet. This will allow you to see busy periods or overlapping tasks. The more tasks you add to the table, the bigger the Gantt chart will become. You can format the chart by clicking on the axes e.g. to change the date range. There are drop down menus within the cells in column B and I. When you select an option, the colour will change automatically. These options are linked to the 'Dropdown Key - Do Not Delete' sheet so don't get rid of that sheet or the dropdwon options will stop working. To inform how often to review the project plan, think about how much time people have to spend on the project tasks. E.g. if everyone is spending 3 days a week on progressing the work, then a weekly meeting might work. However, if the tasks are time consuming and those responsible have little time to progress the work, then a bi-weekly or monthly review meeting might be more appropriate. In advance of such meetings, people responsible for tasks might take the time to update the status column.

## EXAMPLE - Project Plan
PROJECT DELIVERY PLAN
| PROJECT NAME | INSERT HERE |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE | INSERT
| PROJECT MANAGER | INSERT HERE |  | 2025-09-02 | 2025-10-10 | 35% | PROBLEM STATEMENT | INSERT
AT RISK | TASK NAME | TYPE | RESPONSIBLE | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Alex B. | 2025-09-03 | 2025-09-13 | 11
Yes | Insert tasks in this column | Training | Frank C. | 2025-09-03 | 2025-09-07 | 5 | Complete
No | Task 2 | User research | Jacob S. | 2025-09-07 | 2025-09-12 | 6 | In Progress
No | Task 3 | Comms | Jacob S. | 2025-09-09 | 2025-09-13 | 5 | Overdue
No | SPRINT 2 |  | Jacob S. | 2025-09-16 | 2025-09-24 | 9
No | Task |  | Alex B. | 2025-09-16 | 2025-09-17 | 2 | Approved
Yes | Task |  | Frank C. | 2025-09-17 | 2025-09-21 | 5 | Needs Review
No | Task |  | Shari W. | 2025-09-22 | 2025-09-24 | 3 | On Hold
No | SPRINT 3 |  | Shari W. | 2025-09-24 | 2025-10-05 | 12
No | Task |  | Alex B. | 2025-09-25 | 2025-09-29 | 5 | Not Started
No | Task |  | Kennedy K. | 2025-09-24 | 2025-10-02 | 9 | Not Started
No | Task |  | Jacob S. | 2025-10-02 | 2025-10-05 | 4 | Not Started
Formulas:
START DATE = MIN([START DATE, row below]:F11)
END DATE = MAX([END DATE, row below]:G11)

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold